## Slide 1
USMC CapDev: Low-Cost Tactical Missile with AI-Enabled IR Seeker
USMC CapDev IR Seeker — Project Status Report
Project Status Report — March 2026
Generated March 20, 2026
13
Total Goals
1
Complete
4
In Progress
0
Team Members

## Slide 2
Executive Summary
USMC CapDev is progressing through critical seeker development phases with mixed momentum. Four tasks are currently in progress (IR YOLO benchmarking, IR intrinsic calibration, Jetson deployment, and DevOps integration) at 40% completion, one task is in review (Odyssey App deployment at 75%), and one task is complete (AI document access pipeline). However, seven tasks remain not started, creating schedule risk: key calibration documentation, Jetson environment validation, YOLO benchmark archival, and end-to-end pipeline testing are all at risk against May–June deadlines. GitLab repositories show active development in flight software optimization and IR web app deployment. Immediate focus required on Jetson Nano hardware integration and completion of seeker validation tasks to meet critical path milestones.
Goal Status
Chart: 
| Not Started | In Progress | In Review | Complete
Status | 6 | 4 | 2 | 1
8%
Complete

## Slide 3
Goal Progress Overview
Chart: 
| Benchmark and validate IR … | Install and verify IR suit… | Finalize and archive IR in… | Fix IR Intrinsic Calibration | Onboard all GitLab contrib… | Add all Digital Trident Gi… | Validate Jetson environmen… | Enable AI document content… | Document and archive IR YO… | Deploy Odyssey App | Run and verify full IR int… | Validate IR intrinsic cali… | IR Web App integration tes…
Progress % | 40 | 0 | 0 | 40 | 40 | 0 | 0 | 100 | 0 | 75 | 0 | 40 | 80
Category
Seeker
DevOps
Admin
32%
Avg Progress
1 / 13
Done

## Slide 4
Progress by Category
Chart: 
| Seeker | DevOps | Admin
Avg Progress % | 15 | 49 | 100
Category Detail
Seeker
15% avg • 8 goals • 0 done
DevOps
49% avg • 4 goals • 0 done
Admin
100% avg • 1 goal • 1 done

## Slide 5
Task Status Overview & Progress Breakdown
Across the 13 tracked tasks for the period 2025-09-21 to 2026-03-21, one task is Complete (8%), three are In Progress (23%), two are In Review (15%), and seven are Not Started (54%). The sole completed task — 'Enable AI document content access via text extraction pipeline' — was delivered at 100% by its 2026-04-15 deadline. The majority of open tasks are concentrated in the Seeker subsystem, representing the highest area of schedule risk heading into Q2 2026.
Task (Abbreviated) | Status | Progress | Due Date
AI Doc Text Pipeline | COMPLETE | 100% | 2026-04-15
IR Web App QA | IN REVIEW | 80% | 2026-05-30
Deploy Odyssey App | IN REVIEW | 75% | 2026-06-27
IR YOLO Benchmarking | IN PROGRESS | 40% | 2026-05-30
Fix IR Intrinsic Calib. | IN PROGRESS | 40% | 2026-05-30
Validate IR Calib. Pipeline | IN PROGRESS | 40% | 2026-05-30
Onboard GitLab Contributors | IN PROGRESS | 40% | 2026-04-30
Add DT GitLab Contributors | NOT STARTED | 0% | 2026-04-30
Install IR Suite on Jetson | NOT STARTED | 0% | 2026-05-01
Validate Jetson Env Setup | NOT STARTED | 0% | 2026-05-22

## Slide 6
Schedule Risk Assessment & Deadline Status
Of the 13 active tasks in the USMC CapDev project, only 1 task (8%) is fully complete as of the report period ending 2026-03-21, while 4 tasks remain Not Started and 4 are In Progress at 40% completion. The heaviest concentration of deadlines falls between 2026-04-30 and 2026-06-15, creating a late-stage schedule compression risk given the low overall completion rate.
Task (Abbrev.) | Status | Progress | Due Date
AI Doc Content Access | COMPLETE | 100% | 2026-04-15
IR Web App QA | IN_REVIEW | 80% | 2026-05-30
Deploy Odyssey App | IN_REVIEW | 75% | 2026-06-27
Onboard GitLab Contributors | IN_PROGRESS | 40% | 2026-04-30
Fix IR Intrinsic Calib. | IN_PROGRESS | 40% | 2026-05-30
Validate IR Calib. (Jetson) | IN_PROGRESS | 40% | 2026-05-30
Benchmark IR YOLO Metrics | IN_PROGRESS | 40% | 2026-05-30
Add DT GitLab Contributors | NOT_STARTED | 0% | 2026-04-30
Install IR Suite (Jetson) | NOT_STARTED | 0% | 2026-05-01
Validate Jetson Env Setup | NOT_STARTED | 0% | 2026-05-22

## Slide 7
Technical Accomplishments & Repository Activity
Between September 2025 and March 2026, the Digital Trident team produced meaningful technical output across two GitLab repositories — digital-trident-ir-camera-suite and digital-trident-flight-software — with 5 and 10 commits respectively. Key contributors include 1st Lt Kyle Hicks (IR suite documentation and web app integration), Maj Dillon Pierce (flight software system optimization and service configuration), and alex-cv-pi (inference engine, smart zoom, and benchmarking infrastructure). The working IR Web App was committed on 2026-01-20, and flight software reached a stable flight configuration state by 2025-12-10, with CPU affinity and system optimizations finalized by 2026-01-23.
Repo | Commits | Key Contributor | Last Commit
ir-camera-suite | 5 | 1Lt Hicks / Maj Pierce | 2026-03-18
flight-software | 10 | alex-cv-pi / dtpierce | 2026-01-23

## Slide 8
Seeker Development & Calibration Progress
The IR Camera Suite was formally committed to GitLab on 2026-01-20 by 1st Lt Kyle Hicks and Maj Dillon Pierce, establishing a Flask-based web application targeting the RPX EmbIR 640 camera on Jetson Nano hardware. Calibration data shows iterative improvement, with optical center calculations progressing from a 'poor' confidence run (0.44 confidence, 2025-12-15T14:50) to an 'excellent' confidence run (1.0 confidence, 2025-12-15T14:55), though IR-specific intrinsic calibration tasks remain at 0–40% completion. Five YOLO inference pipelines (Basic, Max Speed, Minimal, Thermal Mask, and Simple RPX Feed) are integrated in the web app but hardware validation on Jetson Nano has not yet started.
Task | Status | Progress | Due Date
Fix IR Intrinsic Cal. | IN_PROGRESS | 40% | 2026-05-30
Validate Cal. Pipeline (Jetson) | IN_PROGRESS | 40% | 2026-05-30
Run Full Cal. End-to-End | NOT_STARTED | 0% | 2026-05-30
Install IR Suite (Jetson) | NOT_STARTED | 0% | 2026-05-01
Validate Jetson Env. | NOT_STARTED | 0% | 2026-05-22
Benchmark IR YOLO Metrics | IN_PROGRESS | 40% | 2026-05-30
Archive YOLO Benchmark Results | NOT_STARTED | 0% | 2026-06-15
Finalize Cal. Documentation | NOT_STARTED | 0% | 2026-06-01

## Slide 9
DevOps & Deployment Status
The Odyssey App deployment (task def251b1) is IN_REVIEW at 75% completion against a due date of 2026-06-27, while IR Web App integration testing (task 2638028d) is IN_REVIEW at 80% complete with a 2026-05-30 deadline. Two GitLab contributor onboarding tasks remain at risk: 'Onboard all GitLab contributors as Odyssey project members' is 40% complete and 'Add all Digital Trident GitLab contributors' is 0% complete, both due 2026-04-30.
Task | Status | Progress | Due Date
Deploy Odyssey App | IN_REVIEW | 75% | 2026-06-27
IR Web App QA | IN_REVIEW | 80% | 2026-05-30
Onboard GitLab Users | IN_PROGRESS | 40% | 2026-04-30
Add DT Contributors | NOT_STARTED | 0% | 2026-04-30

## Slide 10
Risks, Issues & Recommendations
Of the 13 tasks in the reporting period, 8 are either Not Started (0%) or at early In-Progress stages (40%), creating a significant backlog risk ahead of deadlines concentrated in May–June 2026. The IR calibration pipeline shows recurring instability — calibration confidence dropped to 0.44 (rated 'poor') on 2025-12-15 before recovering to 1.0 ('excellent') the same day, indicating the process is not yet stable or repeatable on Jetson hardware. DevOps team onboarding remains split across two overlapping tasks (both due 2026-04-30), suggesting process fragmentation that could delay repository access for contributors.
Task (Abbreviated) | Status | Due Date | Risk Level
Jetson Env Setup & Verify | NOT STARTED | 2026-05-22 | HIGH
IR Intrinsic Calib Pipeline | NOT STARTED | 2026-05-30 | HIGH
Install IR Suite on Jetson | NOT STARTED | 2026-05-01 | HIGH
Onboard GitLab Contributors | IN PROGRESS 40% | 2026-04-30 | MEDIUM
Add DT GitLab Contributors | NOT STARTED | 2026-04-30 | MEDIUM
Archive IR Calib Docs | NOT STARTED | 2026-06-01 | MEDIUM
YOLO Benchmark & Archive | NOT STARTED | 2026-06-15 | LOW
Deploy Odyssey App | IN REVIEW 75% | 2026-06-27 | LOW